## High Level Estimates
Sl No | Task | Estimates(days)
1 | Requirements Gathering | 2
2 | Application Foundation * | 2 |  |  | * It includes common components like utility classes, Exception Handling & Security Implementation.
3 | Page Template ** | 4 |  |  | ** It includes Initial Skinning, Initial CSS setup, page Template
4 | Initial Security Setup in the application | 2 |  | Note | * All the estimates are in days.
5 | Development - Modules
| a. Login page | 4
b. User Main Interface
| c. Dashboard | 12 | Assuming that the dashboard has only reporting stuff
| d. Buy/Sell Screen | 8
| e. Data Entry Screen | 8
6 | Responsive | 3
| Total(Days) | 45
Pricing
| Number of hours | 360
| Price per hour | 750
| Total Amount | 270000

## Sample Estimation
The following points were considered before estimating the efforts involved:
1 | All the screens were considered as medium complex with fields ranging from 3 to 25 and having very few inter dependant fields.
2 | UI validation: None of the screen has any complex validations.
3 | As per the client, the model will be database.
5 | All the transactions are limited to one page.
6 | Total estimated hours for any flow can be break down as: Design - 10% Development - 70% Unit Testing - 20%
Example | User Registration Process
|  | Screens | UI Fields | Validation | Estimates | Model | Estimates | Total
|  | Screen -1 | 22 | 8 | 16 | 1 | 6 | 22
|  | Screen-2 | 6 | 2 | 5 | 1 | 6 | 11
|  | Screen-3 | 2 | 2 | 3 | 1 | 6 | 9
|  | Screen-4 | 2 | 2 | 3 | 1 | 6 | 9
|  | Screen-5 | 2 | 2 | 3 | 1 | 6 | 9
[7 empty] | Total | 60
Quotes*
|  | Screens | UI Fields | Validation | Estimates | Model | Estimates | Total
|  | Screen -1 | 14 | 7 | 12 | 0 | 0 | 12
|  | Screen-2 | 25 | 7 | 16 | 2 | 12 | 28
|  | Screen-3 | 12 | 3 | 8 | 1 | 6 | 14
|  | Screen-4 | 12 | 3 | 8 | 1 | 6 | 14
|  | Screen-5 | 2 | 1 | 2 | 1 | 6 | 8
|  | Screen-6 | 5 | 3 | 3 | 1 | 6 | 6
|  | Screen-7 | 20 | 7 | 14 | 1 | 6 | 20
|  | Screen-8 | 18 | 5 | 13 | 2 | 12 | 25
|  | Screen-9 | 24 | 7 | 16 | 2 | 12 | 28
|  | Screen-10 | 12 | 3 | 8 | 1 | 6 | 14
|  | Screen-11 | 11 | 5 | 9 | 1 | 6 | 15
|  | Screen-12 | 15 | 3 | 10 | 1 | 6 | 16
|  | Screen-13 | 17 | 5 | 12 | 0 | 0 | 0
[7 empty] | Total | 200
* All the above estimates are in days.
* This is the most complex screen

## Assumptions
Sl No | Basic Assumptions
1 | Infrastructure setup is not in scope
2 | Functional Testing, Integration Testing etc are not in scope, only Unit Testing is covered.
3 | Load Testing is not in scope, but the pages will be tuned to perform efficiently.
4 | We will leverage existing backend services wherever applicable.
5 | Deliverable will be – Web application deployed on the server, Source code.
6 | I will be developing the application on my laptop. If required can connect to your database using VPN.
7 | You will provide the testing environment if required.
8 | Before starting the development, all requirements, UI to be formally freezed.
9 | All business validation will be provided along with mockup.
10 | Estimate doesn’t include time for Data modeling, business logic, webservice development. It’s assumed that we can use component from existing project , any deviation from that is not in scope.
11 | Build Script , Deployment Automation or Continuous Integration is not part of estimate.
12 | Assumption is that application will be developed with Out of box capability of Oracle ADF
13 | Assumption is that multi language is not supported by the portal.
14 | Documentation efforts are not included in the scope
15 | Hardware installation efforts are not included in the scope.
16 | Need mockups/wireframes for all the devices.

## Additional Questions
Sl No | Questions
1 | Screens needs to be discussed in detail
2 | Security requirements
3 | Backend needs to be discussed
4 | Let us know the version of ADF/Jdeveloper to be used.
5 | Is there a forgot password page as well?
6 | Against what the authentication is done?
7 | What is the security model?
8 | The dashboard boxes are they independent functionality or only reporting stuff